## Sheet1
Stages
Staff
| Planning | Designing | Developing | Testing | Implementing | Total
| (4 weeks) | (5.43 weeks) | (11 weeks) | (1 week) | (1 week) | Time
Project Manager | 50.0 hours | 80.0 hours | 198.0 hours | 30.0 hours | 30.0 hours | 388 hours
Shaun Ibañez | 4week | 5.43week | 11week | 1week | 1week
Documentation | 50.0 hours | 80.0 hours | 198.0 hours | 30.0 hours | 30.0 hours | 388 hours
Krisper Bariuan | 4week | 5.43week | 11week | 1week | 1week
System Analyst | 50.0 hours | 80.0 hours | 198.0 hours | 30.0 hours | 30.0 hours | 388 hours
Zian Vertudes | 4week | 5.43week | 11week | 1week | 1week
Q.A. Staff | 50.0 hours | 80.0 hours | 198.0 hours | 30.0 hours | 30.0 hours | 388 hours
Buena Talosig | 4week | 5.43week | 11week | 1week | 1week